## Finances
Budget
Venue Costs
Rental Space
Set-up or Cleaning Charges
AV
Coat Check
Event Insurance
Food Service
Number of people
Cost per person
Waitstaff + Tips
Service Charges
Equipment
Canopy/Tent
Backdrop
Décor
Table/Chairs
Flooring/Carpeting
Risers
Podium
Registration Tables
Booths
Easels
Delivery
Design & Printing
Save the Date
Invitations
Programs
Agendas
Tickets
Name Badges and Holders
Table Numbers
Awards
Instructions
Lists
Postage & Shipping
Postage for mailed or printed materials
Shipping charges to site
Transportation
Shuttles
Valet
AV Equipment
Projectors
Screens
Extension cords
Projector Cart
Microphones
Mizers
Speakers
Computer
Pointer/Remote
Flip Chart
Technician
Wi-Fi
Entertainment
Fees
Hospitality
Equipment needed
Supplies
Pens/Paper/Notepads
Folders
Miscellaneous
Speaker travel expenses
Volunteer expenses
Honoraria
Gifts
Mementos//giveaways
Security
Recording
Comp tickers
Wi-Fi
Raffle Prizes

## Volunteers
Volunteers
Communication
Speaker Recruitment/selection
Agenda Topics and Titles
Contracts
On-site | Set-up
Greeters
Registration desk
Moderator
Speaker handler
F&B Contact
Photographer
Social Media
Vendor Manager

## Project list sheet
<Event Name Here>
| Task Name | Assigned | State | Status | Due Date | Budget | Actual Cost | Comments
Event Total |  |  |  |  | 2010-09-08 | 5400 | 0
Event Theme - Name, Logo, Designs |  |  |  | In Progress | 2013-09-16 | 4000 | 0
| Develop Event Theme | Bob | Green | Complete | 2013-09-16 | 2750 | 0
| Develop tagline | Sue | Green | Complete | 2013-09-16 | 1250 | 0
| Develop colors/images | Sue | Green | In Progress | 2013-09-16
| Decide on "main event" | Bob | Red | In Progress | 2013-09-16 |  |  | Still split on which event is "main"
| Awards ceremony | Bob | Green | Decided Against | 2013-09-16
| Presentation | Sue | Green | In Progress | 2013-09-16
| Select MC | Sue | Green | Complete |  |  |  | Susan will be the M.C.
Collateral and Promotion |  |  |  | In Progress | 2013-09-29 | 1000 | 0
| Banners | Sue | Yellow | In Progress | 2013-09-29 | 1000
| Hanging Banners Design | Joy | Yellow | Not Started | 2013-09-29
| Hanging Banners Printing | Joy | Yellow | Not Started
Invitations |  |  |  | In Progress | 2013-10-06 | 400 | 0
| Invitation HTML : Design | Joy | Yellow | In Progress | 2013-10-06 | 400
| Invitation HTML: Programming |  |  |  | 2013-10-06
| Reminder HTML: Design |  |  |  | 2013-10-06
| Reminder HTML: Programming |  |  |  | 2013-10-06
| Printed invitation: Design |  |  |  | 2013-10-06
| Printed invitation: Printing |  |  |  | 2013-10-06
Menu Planning and Budget | [5 empty] | 0 | 0
| Hors d'oeuvres (cold) |  |  |  | 2013-10-06
| Hors d'oeuvres (hot) |  |  |  | 2013-10-06
| Appetizer (plated) |  |  |  | 2013-10-06
| Salad |  |  |  | 2013-10-06
| Entree |  |  |  | 2013-10-06
Beverages - cocktail reception | [5 empty] | 0 | 0
| Liquor selections |  |  |  | 2013-10-06
| Beer/wine selections |  |  |  | 2013-10-06
| Sales Tax and Gratuities (5%+19%) |  |  |  | 2013-10-06
Attendee Gifts & Door Prizes | [5 empty] | 0 | 0
| Gift--Themed gift for attendees |  |  |  | 2013-10-06
| Decide on door prizes (AMEX gift certificate?) |  |  |  | 2013-10-06
Entertainment | [5 empty] | 0 | 0
| Find a local talent agency |  |  |  | 2013-10-06
| Pick a local band |  |  |  | 2013-10-06
| Jazz/blues/instrumental |  |  |  | 2013-10-06
| Cover band |  |  |  | 2013-10-06
| Funk band |  |  |  | 2013-10-06
| Tax |  |  |  | 2013-10-06
| Tip |  |  |  | 2013-10-06
Audio Visual | [5 empty] | 0 | 0
| Monitor |  |  |  | 2013-10-06
| Screen |  |  |  | 2013-10-06
| Microphone |  |  |  | 2013-10-06
Miscellaneous | [5 empty] | 0 | 0
| TBD |  |  |  | 2013-10-06
| TBD |  |  |  | 2013-10-06
| For a similar spreadsheet-oriented project tracking approach that is seamless and easy to use, try Smartsheet/ Plus, enjoy capabilities like: • Use Gantt charts to visually track the course of a project, starting from a firm deadline. • Collaborate with team members to manage tasks. • Include discussions and uploaded files on each row. ... plus much more. Follow the link to the left: |  |  |  |  | https://www.smartsheet.com/eveningreception&s=56&c=62
| Or, if your company uses Google Apps, your Google Apps Domain Admin can install Smartsheet into your Google Apps: |  |  |  |  | https://www.google.com/enterprise/marketplace/viewListing?productListingId=3429+4388443950638085375&s=56&c=62
Smartsheet Templates for Event Management