## Slide 1
Event Committee
Reviews Submission
Reminder Notice
Finance
Develops Resource Plan
Marketing
Approved ?
No
Technology
Yes
Event Committee
Submit Work Order
Submits
Request
Sponsor
Finance
Generate Invoice
Paid in Full ?
(10 Days)
No
Paid in Full ?
(10 Days)
Cancel Project
Programming Committee Schedule Project
Yes
One Week
One Week
One Week
Yes
Event Director Identified - Creates Placeholder Request
To Marketing
Create Placeholder on Website
Legend
Sponsor
Programming Committee
Finance Committee
Marketing/Technology Task Force
Event Director Finalizes Presenters and Content
Form 1
Form 2
Form 3
Form 4
At least 1 month prior to Event
Event Director Fills out and Submits E-form to Marketing
Form Marc
Marketing Develops Campaign based on Calendar Timeframes
Creates Registration Link in Star Chapter
Identifies Producer for Event
At least 2 weeks prior to Event
Event Director with Producer schedules Dry Runs
Dry Run 1
Dress Rehearsal
Live Event
At least 1 week prior to Event
At least 1 day prior to Event

## Slide 2: Sample Forms
Sponsor Submitted Request Form to Events Task Force
Title of Event
Abstract of Event
Requested Date of Event
Targeted Membership
Anticipated Benefits to the Chapter
Finance Review and Input
Marketing/Tech Review and Input
Programming Submitted Work Order to Finance
Title of Event
Abstract of Event
Requested Date of Event
Targeted Membership
Anticipated Benefits to the Chapter
Finance Review and Input
Marketing/Tech Review and Input
Finance enters in QuickBooks
  Generates Invoice to Sponsor
  PAID
Programming Submitted Place Holder to Marketing
Title of Event
Abstract of Event
Date of Event
Targeted Membership
Event Director
  Event Task Force Member Responsible for Event
Form 1
Form 2
Form 3
Programming Submitted Place Holder to Marketing
Title of Event
Abstract of Event
Date of Event
Targeted Membership
Presenters
  Headshots
  Bio’s
Form 4